## Learn Excel
Learn More From Our Free Excel Resources:
Webinars: Formulas, Pivot Tables and Macros & VBA
Blog Tutorials: Formulas, Pivot Tables, Charts, Macros, VBA, Power Query, Power Pivot, Analysis
Excel Podcast Interviewing the Excel Experts

## Start
ABOUT THIS TEMPLATE
Use this workbook to track Project Parameters, Project Details, and Project Totals during Project Planning for Law Firms.
Fill in Company Name in Project Parameters worksheet and it is auto updated in other worksheets.
Enter information in Project Parameters worksheet to update column charts, and in Project Details worksheet. PivotTable in Project Totals worksheet is auto updated
Note:
Additional Instructions have been provided in column A of each worksheet. This text has been intentionally hidden. To remove text, select column A, then select DELETE. To unhide text, select column A, then change font color.
To learn more about tables in worksheets, press SHIFT and then F10 within a table, select the TABLE option, and then select ALTERNATIVE TEXT. For PivotTable in Project Totals worksheet, press SHIFT and then F10 within table, select PIVOTTABLE OPTIONS, and then select ALT TEXT tab.

## PROJECT PARAMETERS
Create Project Parameters in this worksheet. Enter Company Name in cell at right. Helpful instructions are in cells in this column. | Company Name
Title of this worksheet is in cell at right. | Project Planning for Law Firms
Confidentiality message is in cell at right. | Company Name Confidential
Tip is in cell at right. | Shaded cells are calculated for you. You do not need to enter anything into them.
Enter details in Parameters table starting in cell at right. Next instruction is in cell A12. | PROJECT TYPE | GENERAL PARTNER | BUSINESS LAWYER | DEFENSE LITIGATOR | INTELLECTUAL PROPERTY LAWYER | BANKRUPTCY LAWYER | ADMIN STAFF | TOTAL
| Business Incorporation | 10% | 40% | 0% | 0% | 0% | 50% | 100%
| Business Acquisition | 10% | 40% | 0% | 10% | 0% | 40% | 100%
| Product Liability Defense | 20% | 0% | 50% | 0% | 0% | 30% | 100%
| Patent Application | 10% | 0% | 0% | 60% | 0% | 30% | 100%
| Employee Lawsuit | 20% | 10% | 40% | 0% | 0% | 30% | 100%
| Bankruptcy | 10% | 20% | 0% | 0% | 40% | 30% | 100%
Enter Blended Rates in cells at right, cells C12 through H12. Next instruction is in cell A14. | Blended rates | 350 | 250 | 300 | 275 | 225 | 125
Column chart showing comparison between Planned and Actual Cost is in cell at right, and column chart showing comparison between Planned and Actual Hours is in cell F14.
|  | GENERAL PARTNER | BUSINESS | DEFENSE LITIGATOR | INTELLECTUAL PROP. | BANKRUPTCY | ADMIN STAFF
| PLANNED COST | 78750 | 66250 | 105000 | 35750 | 0 | 66250
| ACTUAL COST | 79275 | 67375 | 105600 | 34650 | 0 | 67000
| PLANNED HOURS | 225 | 189.2857 | 300 | 102.1429 | 0 | 189.2857
| ACTUAL HOURS | 226.5 | 192.5 | 301.7143 | 99 | 0 | 191.4286

## PROJECT DETAILS
Create Project Details in this worksheet. Company Name is auto updated in cell at right. Helpful instructions are in cells in this column. Arrow down to get started. | Company Name
Title of this worksheet is in cell at right and Info tip in cell Y2 . | Project Planning for Law Firms | [21 empty] | INFO: To add a row, select the bottom-right most cell in the body of the table (not the totals row) and press Tab, or press SHIFT and then F10 within table where you want the row inserted and select Insert ¦ Table Rows Above/Below. Be sure all unused rows are deleted, as the PROJECT TOTALS PivotTable will use all of the tables cells, and otherwise would give erroneous results.
Confidentiality message is in cell at right. | Company Name Confidential
Enter information in Details table starting in cell at right. Project Types in Details table at right are auto updated from Parameters table in Project Parameters worksheet. | PROJECT NAME | PROJECT TYPE | ESTIMATED START | ESTIMATED FINISH | ACTUAL START | ACTUAL FINISH | ESTIMATED WORK | ACTUAL WORK | ESTIMATED DURATION | ACTUAL DURATION | GENERAL PARTNER | BUSINESS LAWYER | DEFENSE LITIGATOR | INTELLECTUAL PROPERTY LAWYER | BANKRUPTCY LAWYER | ADMIN STAFF | GENERAL PARTNER 2 | BUSINESS LAWYER 2 | DEFENSE LITIGATOR 2 | INTELLECTUAL PROPERTY LAWYER 2 | BANKRUPTCY LAWYER 2 | ADMIN STAFF 2
| Project 1 | Business Incorporation | 2019-02-06 | 2019-04-07 | 2019-02-16 | 2019-04-12 | 200 | 220 | 61 | 56 | 7000 | 20000 | 0 | 0 | 0 | 12500 | 7700 | 22000 | 0 | 0 | 0 | 13750
| Project 2 | Business Acquisition | 2019-03-08 | 2019-05-17 | 2019-03-18 | 2019-05-27 | 400 | 390 | 69 | 69 | 14000 | 40000 | 0 | 11000 | 0 | 20000 | 13650 | 39000 | 0 | 10725 | 0 | 19500
| Project 3 | Product Liability Defense | 2019-07-06 | 2019-07-06 | 2019-07-06 | 2019-07-26 | 500 | 500 | 0 | 20 | 35000 | 0 | 75000 | 0 | 0 | 18750 | 35000 | 0 | 75000 | 0 | 0 | 18750
| Project 4 | Patent Application | 2019-08-25 | 2019-09-24 | 2019-09-24 | 2019-09-24 | 150 | 145 | 29 | 0 | 5250 | 0 | 0 | 24750 | 0 | 5625 | 5075 | 0 | 0 | 23925 | 0 | 5437.5
| Project 5 | Employee Lawsuit | 2019-09-14 | 2019-10-14 | 2019-09-24 | 2019-10-23 | 250 | 255 | 30 | 29 | 17500 | 6250 | 30000 | 0 | 0 | 9375 | 17850 | 6375 | 30600 | 0 | 0 | 9562.5
| TOTAL | [5 empty] | 1500 | 1510 | 189 | 174
INFO
To add a row, select the bottom-right most cell in the body of the table (not the totals row) and press Tab, or press SHIFT and then F10 within table where you want the row inserted and select Insert | Table Rows Above/Below.
Be sure all unused rows are deleted, as the PROJECT TOTALS PivotTable will use all of the tables cells, and otherwise would give erroneous results.
To delete this info tip, select any edge and press Delete.

## PROJECT TOTALS
Get Project Totals in this worksheet. Company Name is automatically updated in cell at right. Helpful instructions are in cells in this column. Arrow down to get started. | Company Name
Title of this worksheet is in cell at right. | Project Planning for Law Firms
Confidentiality message is in cell at right. | Company Name Confidential
Estimated label is in cell C4, Actual label in cell I4, and Info tip in cell P4. |  | ESTIMATED | [5 empty] | ACTUAL | [5 empty] | INFO: This PivotTable will not refresh automatically. To refresh it, select it (any cell within the PivotTable), on the PIVOTTABLE TOOLS ¦ ANALYZE ribbon tab select Refresh. Or press SHIFT + F10 by selecting the PivotTable and select Refresh.
PivotTable starting in cell at right is auto updated | PROJECT NAME | GENERAL PARTNER | BUSINESS | DEFENSE LITIGATOR | INTELLECTUAL PROPERTY | BANKRUPTCY | ADMIN STAFF | GENERAL PARTNER | BUSINESS | DEFENSE LITIGATOR | BANKRUPTCY | INTELLECTUAL PROPERTY | ADMIN STAFF
| Project 1 | 7000 | 20000 | 0 | 0 | 0 | 12500 | 7700 | 22000 | 0 | 0 | 0 | 13750
| Project 2 | 14000 | 40000 | 0 | 11000 | 0 | 20000 | 13650 | 39000 | 0 | 0 | 10725 | 19500
| Project 3 | 35000 | 0 | 75000 | 0 | 0 | 18750 | 35000 | 0 | 75000 | 0 | 0 | 18750
| Project 4 | 5250 | 0 | 0 | 24750 | 0 | 5625 | 5075 | 0 | 0 | 0 | 23925 | 5437.5
| Project 5 | 17500 | 6250 | 30000 | 0 | 0 | 9375 | 17850 | 6375 | 30600 | 0 | 0 | 9562.5
| Grand Total | 78750 | 66250 | 105000 | 35750 | 0 | 66250 | 79275 | 67375 | 105600 | 0 | 34650 | 67000
INFO
This PivotTable will not refresh automatically. To refresh it, select it (any cell within the PivotTable), on the PIVOTTABLE TOOLS | ANALYZE ribbon tab press Refresh. Or press SHIFT and then F10 within the PivotTable and select Refresh.
To delete this info tip, select any edge and press Delete.